## Risk Register
Risk ID | AI System Name | Risk Category | Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Existing Controls | Residual Risk | Mitigation Plan | Owner | Status | Review Date
RISK-001 | AI Hiring Screening Tool | Bias/Fairness | The AI model may discriminate against candidates based on gender, race, or age due to biased historical training data | 4 | 5 |  | Quarterly bias audits conducted by HR team | High | Engage third-party auditor for independent bias testing. Retrain model on balanced dataset. Implement fairness metrics dashboard | HR Director | Open | 30-Jun-2025
RISK-002 | AI Hiring Screening Tool | Privacy/Data Protection | System collects and processes candidate personal data without explicit informed consent, violating GDPR and CCPA regulations | 3 | 5 |  | Privacy policy displayed during application process | High | Implement explicit consent mechanism. Conduct privacy impact assessment. Appoint data protection officer | Legal Counsel | Open | 30-Jun-2025
RISK-003 | AI Hiring Screening Tool | Transparency/Explainability | Candidates are rejected by the AI with no explanation provided, making it impossible to appeal or understand the decision | 4 | 4 |  | None currently in place | High | Implement explainability module. Provide candidates with rejection reasoning. Create appeal process | Product Manager | Open | 31-Jul-2025
RISK-004 | AI Hiring Screening Tool | Security/Adversarial | Malicious actors could manipulate candidate resumes with hidden keywords to game the AI screening algorithm | 3 | 4 |  | Basic input validation on resume uploads | Medium | Implement adversarial testing program. Add anomaly detection for unusual resume patterns. Regular penetration testing | Security Team | In Progress | 31-Jul-2025
RISK-005 | AI Hiring Screening Tool | Legal/Regulatory | AI hiring tool may violate Equal Employment Opportunity laws by systematically filtering out protected class candidates | 3 | 5 |  | Legal review conducted at initial deployment | High | Engage employment law specialist. Conduct disparate impact analysis quarterly. Document all compliance measures | Legal Counsel | Open | 30-Jun-2025
RISK-006 | AI Hiring Screening Tool | Reliability/Performance | AI model performance degrades over time as job market language and resume formats evolve, leading to poor candidate matching | 4 | 3 |  | Annual model review scheduled | Medium | Implement continuous model monitoring. Set performance thresholds with automatic alerts. Schedule quarterly retraining | ML Engineering Team | In Progress | 31-Aug-2025
RISK-007 | AI Hiring Screening Tool | Reputational | Media coverage of biased AI hiring decisions could damage company brand and reduce quality candidate applications | 2 | 5 |  | PR crisis communication plan exists | Medium | Proactively publish AI ethics policy. Engage with diversity advocacy groups. Create transparency report annually | Communications Director | Open | 31-Aug-2025
RISK-008 | AI Hiring Screening Tool | Operational | Over-reliance on AI screening reduces human oversight, causing qualified candidates to be rejected without any human review | 4 | 4 |  | HR team reviews final shortlist | High | Mandate human review for all AI rejections above seniority level 3. Implement human-in-the-loop checkpoints | HR Director | Open | 30-Jun-2025
RISK-009 | AI Hiring Screening Tool | Bias/Fairness | AI model penalizes resume gaps which disproportionately affects women who took maternity leave or caregiving breaks | 4 | 4 |  | No specific control in place | High | Remove employment gap as a negative signal. Retrain model. Add specific fairness test for this scenario | ML Engineering Team | Open | 31-Jul-2025
RISK-010 | AI Hiring Screening Tool | Security/Adversarial | Unauthorized access to candidate database could expose personal information of thousands of applicants | 2 | 5 |  | Database encrypted at rest. Access logs maintained | Medium | Implement role-based access control. Conduct annual security audit. Add multi-factor authentication for all admin access | Security Team | In Progress | 30-Jun-2025
RISK-011 | AI Hiring Screening Tool | Legal/Regulatory | New EU AI Act classifies AI hiring tools as high-risk requiring mandatory conformity assessment before deployment | 5 | 5 |  | Monitoring regulatory developments | Critical | Engage EU AI Act compliance specialist. Begin conformity assessment process. Allocate budget for compliance program | Legal Counsel | Open | 31-May-2025
RISK-012 | AI Hiring Screening Tool | Transparency/Explainability | Hiring managers do not understand how the AI scores candidates, leading to blind trust in AI recommendations | 4 | 3 |  | Basic user guide provided at onboarding | Medium | Develop comprehensive AI literacy training for all hiring managers. Create dashboard showing AI decision factors | Training Department | In Progress | 31-Aug-2025
RISK-013 | AI Hiring Screening Tool | Reliability/Performance | AI system experiences downtime during peak hiring season causing significant delays in recruitment pipeline | 3 | 3 |  | 99.5% uptime SLA with vendor | Low | Implement manual backup screening process. Define escalation path for system outages. Test failover procedures | IT Operations | Open | 30-Sep-2025
RISK-014 | AI Hiring Screening Tool | Privacy/Data Protection | Candidate data retained indefinitely after hiring decision violating data minimization principles under GDPR | 3 | 4 |  | No formal data retention policy exists | High | Create and implement data retention policy. Automate deletion of candidate data after 12 months. Document compliance | Data Protection Officer | Open | 30-Jun-2025
RISK-015 | AI Hiring Screening Tool | Operational | No formal incident response plan exists if the AI system produces discriminatory outputs at scale | 3 | 5 |  | General IT incident response plan in place | High | Develop AI-specific incident response playbook. Define roles and responsibilities. Conduct tabletop exercise annually | Risk Manager | Open | 31-May-2025

## Scoring Guide
AI Risk Register — Scoring Guide & Methodology
LIKELIHOOD SCALE | Definition | IMPACT SCALE | Definition
1 | Rare — May occur only in exceptional circumstances | 1 | Minimal — Negligible effect on operations or stakeholders
2 | Unlikely — Could occur at some time | 2 | Minor — Small effect, easily managed
3 | Possible — Might occur at some time | 3 | Moderate — Significant effect requiring management attention
4 | Likely — Will probably occur in most circumstances | 4 | Major — Significant harm to individuals or organization
5 | Almost Certain — Expected to occur in most circumstances | 5 | Catastrophic — Severe harm, regulatory action, or existential threat
RISK SCORE HEAT MAP (Likelihood × Impact)
1–5 | LOW RISK |  | Acceptable — Monitor annually
6–14 | MEDIUM RISK |  | Tolerable — Manage and monitor quarterly
15–25 | HIGH RISK |  | Unacceptable — Immediate action required

## Risk Categories
AI Risk Categories — Reference Guide
Risk Category | Description & Examples
Bias/Fairness | Risks that the AI system produces outputs that discriminate against protected groups. Includes training data bias, proxy discrimination, and disparate impact on race, gender, age, or disability.
Security/Adversarial | Risks from malicious attacks on the AI system including adversarial inputs, model inversion attacks, data poisoning, and prompt injection. Also covers unauthorized access to AI model weights or training data.
Privacy/Data Protection | Risks related to collection, processing, or storage of personal data without consent or legal basis. Includes GDPR/CCPA violations, data minimization failures, and re-identification risks.
Reliability/Performance | Risks that the AI system fails to perform as expected including model drift, system outages, accuracy degradation, and failure under edge cases or distribution shift.
Transparency/Explainability | Risks arising from lack of interpretability in AI decisions. Includes inability to explain decisions to affected parties, black-box models in high-stakes contexts, and lack of auditability.
Legal/Regulatory | Risks of non-compliance with applicable laws and regulations including EU AI Act, EEOC guidelines, sector-specific regulations, and emerging AI legislation globally.
Operational | Risks to business operations including over-reliance on AI, lack of human oversight, inadequate incident response, vendor dependency, and integration failures with existing systems.
Reputational | Risks to organizational reputation from AI failures including negative media coverage, public backlash, loss of customer trust, and association with harmful AI outcomes.